## Product Backlog
Product Backlog - iRevatureTrainingRoomMaintenanceScheduler
Totals:
User Story | Pre-Condition | Acceptance Criteria | Assigned To | Status | Hours/Points
As a User I want to put in my email and password and click submit in-order to login. | User Database | Character Limit - 15 | Dane |  | 2
| User already exists | Email and Password return an authenticated token
As a User, if I forgot my password I should be able to click a link to reset my password. | User database | Valid email address is submitted | Dane |  | 2
User already exists
As a Site Manager, I want to select a training room to view its maintenance schedule history | Room Database | Current user is authenticated as a valid site manager | Mark |  | 4
Calendar and rooms are valid for current user
As a User, I want to update the maintenance schedule for a selected room. | Room Database | Selected maintence task exist for the schedule | Kyle |  | 3
Maintence Task
As a Site Manager, I can add or remove a new task to a maintenance schedule. | Room Database | User has permissions to add or remove tasks which need to be completed for their location | Mark |  | 3
As a Site Manager, I should be able to view a maintance log that I can save in another format so I can share that documentation with parties who do not have access to Revature | Room Database | User is permitted to view all training room data for their assigned location | Mark |  | 5
Able to access maintenance calendars
As a trainer, I want to view the rooms which are assigned to me so that I may update their maintenance schedule | Training batch database | User is a valid trainer assigned to a batch with specified room | Kyle |  | 4
Room database
Note on A4: User Story: There may be more than one task for each user story - fill this column out so you can filter by User Story
Note on B4: Developer: Which Team member is leading on this task?
Note on F4: Hours/Points: How many units (points/hours) estimated against this task at the beginning of the sprint